## Slide 1: The EMP evaluation process 2010-2012 External Evaluator: Camilla Badstübner-Kizik Institute of Applied Lingustics / Culture and Media Didactics in Foreign Language Teaching University of Poznan, Poland

## Slide 2: The EMP evaluation process
Evaluation Agenda
Evaluating the process of developing EMP
Evaluating the deliverables of EMP
Achievements
Problems / questions

## Slide 3: 1. Evaluation Agenda May 2010 – September 2012
Independant Consultant (02/10 – 11/10)
Call for bids (11/10)
Final evaluation plan / contract (01/11)
8 evaluation steps
1-3) Discussing & developing project deliverables
May 2010 – March 2011
    a) Project meetings
    b) MOODLE
4) Progress Report
March 2011
5-8) Piloting & reshaping project deliverables
April 2011 – June/July 2012
        a) Project partners - Pilot teachers
        b) Pilot teachers - Teachers
Final Report
October 2012

## Slide 4
Teacher’s Handbook / Booklet, Pupil’s Music Portfolio,
Core activities / Activity database ,
Comenius CPD Courses/National EMP-L courses,
Project website / MOODLE,
Project Newsletters

## Slide 5: 2. Evaluating the process of developing EMP
Project meetings
    running of discussion / impact on deliverables
    actual project meetings
Online discussion
    activity
    display of results

## Slide 6: a) Project meetings (SG + BE)
Place | Time | Feedback (number of responses)
DE Ochsenhausen | 10/09 (Kick off-meeting) | 17
GB Canterbury | 02/10 | 7
GB Edinburgh | 05/10 | 20
GR Athens | 11/10 | 14
RO Constanta | 04/11 | 8
ES Barcelona | 11/11 | 16
CH Schiers | 07/12 | 2

## Slide 7: Feedback on project meetings
Running of discussion / impact on deliverables
+ gradually improving
+ (more or less) meaningful results
- vague / hardly comparable answers
Actual project meetings
  + creative atmosphere
  + place / contacts
  + improvement in communication & management
  high time pressure / tight schedule
  finances
  certain imbalance of activities

## Slide 8: Developing AG, TH, PMP: online discussion
Main activities
10/2010 - 07/2011
AG: 2 responses
TH: 14 responses
PMP: 2 responses
Theoretical background: 1-2 responses

## Slide 9: 3. Evaluating the deliverables of EMP
Teacher’s Handbook / Teacher’s Booklet
Pupil’s Music Portfolio
Core activities / Activity database - MOODLE
Comenius CPD Courses / National EMP-L Courses
Project website / MOODLE
Project Newsletters (1-4)

## Slide 10: a) Teacher’s Handbook drafts 1-5 final version 02/12, booklets?

## Slide 11: Developing the TH: project meeting RO, Constanta 04/11, 8 x
Completeness?
Transparency?
Comprehensiveness?
Linking S-P approach?
Needs of MT?
Needs of LT?
Missing?
Other aspects?

## Slide 12: Feedback on TH ,outside’ feedback (9x)
+ Clear structured / comprehensive!
+ Easy to use / helpful!
+ Good link between theory and classroom work!
+ Inspiring creativity!
Summary / short version?
Balance between linguistic and musical aims and teaching competences?
Other languages than primary English?
Feedback from pilot teachers / teachers?
National language versions / booklets?

## Slide 13: b) Pupil’s Music Portfolio several drafts final version 03/12
My Musical Journal
10 sections, 1-5 cards (46)
opportunities for musical / language learning
linking with TH, references to ELP
suggested extensions for (inter)cultural awareness
sample activities
suggested learning strategies
Music and me
12 cards (pupil’s and teacher’s cards), different activities
linking with TH and MMJ
suggested extensions for (inter)cultural awareness
sample activities
My Musical Treasure
sample card for portfolio

## Slide 14
MMJ

## Slide 15
MaM

## Slide 16: Feedback on PMP 06/12 – 09/12?
+ clear coherent structure and linking!
+ careful design!
+ main areas of activities covered!
+ inspiring creativity!
balance between musical and linguistic activities?
target group(s)?
  multilingual classroom in a second language setting?
  strong elements of CBLL and CLIL?
Teacher’s and pupil’s feedback?
Pupil’s portfolio cards in national languages?

## Slide 18: c) Core activities / Activities Database online 14/09/12
6 free
activities
about 100 activities with restricted access

## Slide 19: d) Comenius CPD Courses / National EMP-L Courses 14/09/2012
CPD courses (members of BE/SG, multinational participants, 2,5-5 days stucture)
  2010: 1
  2011: 2
  2012: 10
  2013: 8
National EMP-L Courses (pilot teachers)
  2010: 3
  2011: 4
  2012: 7
  2013: 3

## Slide 20: Feedback on CPD / EMP-L courses
Time | Place |  |  | Feedback (number of responses)
2010, 09/09 | DE, Suttgart | EMP-L |  | -
2010, 18/09 | GB, Edinburgh | EMP-L |  | -
2011, 26-28/04 | DE, Ochsenhausen |  | CPD | -
2010, 22/09 +11/11 +14/02 + 12/05 + 05/072012 | ES, Cerdanyola del Valles | EMP-L |  | -

## Slide 21
Time | Place |  |  | Feedback (number of responses)
2011, 12/02 | GB, Edinburgh | EMP-L |  | 
2011, 14/02 +12/05 +05/07 | ES, Cerdanyola del Valles | EMP-L |  | 
2011, 04-06/04 | DE, Ochsenhausen | EMP-L |  | 12
2011, 24/05 | DE, Bad Saulgau |  | CPD | 
2011, 08/09 +26/10 +11/01 +08/03 +24/04 +04/07/2012 | ES, Cerdayola del Valles | EMP-L |  | 
2011, 09+16/11 + 08/02/2012 | DE, Stuttgart |  | CPD | 6

## Slide 22
Time | Place |  |  | Feedback (number of responses)
2012, 12 /01 | DE, Stuttgart |  | CPD | 
2012, 18-22 /01 | DE, Ochsenhausen |  | CPD | 10
2012, 02+09/02 + 26/04 | FIN, Lahti | EMP-L | CPD | 4
2012, 05+09+30/03 | GB, Edinburgh | EMP-L |  | 
2012, 10/03 | CH, Aarau | EMP-L |  | 
2012, 12-14/03 | DE, Ochsenhausen |  | CPD | 7
2012, 24/03, 16/05, 13/06 | CH, Aarau | EMP-L |  | 
2012, 02+04+06/04 | RO, Constanta |  | CPD | 3
2012, 08/05 | DE, Nagold | EMP-L | CPD | 
2012, 23-25/05 | DE, Bad Wildbad |  | CPD | 16
2012, 19-24/06 | GB, Canterbury |  | CPD | 20
2012, 29-30/06 | GB, Edinburgh | EMP-L |  | 
2012, 08-13/07 | CH, Schiers |  | CPD | 8
2012, 03-08/09 | ES, Barcelona |  | CPD | 

## Slide 23: Upcoming CPD / EMP-L courses
Time | Place |  | 
2012, 22/08 +14/11 +23/01 +13/03 2013 | CH, Aarau | EMP-L | 
2012, 22/09 +12/12 +16 /01 2013 | CH, Aarau | EMP-L | 
2012, 26/09 | DE, Stuttgart |  | CPD
2012, 22-16/10 | FR, Montpellier |  | CPD
2012, 25/10 | DE, Stuttgart / Esslingen |  | CPD
2012, 14/11 | DE, Stuttgart |  | CPD
2012, 05-09/12 | GR, Athens |  | CPD
2013, 06/02 | DE, Stuttgart | EMP-L | CPD
2013, 13-15/02 | DE, Bad Wildbad |  | CPD
2013, 20-22/03 | DE, Ochsenhausen |  | CPD

## Slide 24: Feedback on CPD / EMP-L courses: Canterbury (GB) 06/2012, Schiers (CH) 07/2012
+ (very) inspiring / positive experience
+ contacts
+ materials / ideas
tight schedule?
theory load?
unbalanced musical – linguistic input?
language choice?

## Slide 25: e) Project website / MOODLE

## Slide 26: Open space 14/09/2012
- TH (+ PMP)
6 free activities
flyers in 8 languages
10 publications
congress Mannheim October 2011
Kick off-presentation, 19th EAS Conference
191 scientific references (03/2011)
training courses
EU report on Creativity and Innovation in Education (12/2010)
5 short sequences of rhythmic exercises in a German speaking EFL class

## Slide 27: Restricted area 14/09/2012

## Slide 28: Restricted area 14/09/2012

## Slide 29: Feedback on project website occasionally from BE/SG project meeting RO, Constanta 04/11, 8 x
Frequency / aim of usage / expectations

## Slide 30: f) Project Newsletters 1 (03/12), 2 (04/12), 3 (08/12), 4 (09/12), upcoming 5+6

## Slide 31
4. Achievements
Professional networking
creativity
interdisciplinarity
Deliverables
close cooperation research-teaching
strong impulse for CPD
sound foundation for follow-up projects
TH / PMP: rich source for scientific evidence and its practical application: starting point / treasure chest
5. Problems/questions
Issues of organisation
flow of communication
task allocation and coordination
online presence (public access, copyright …)
Issues of content
balance between Music and Foreign Language Teaching / Learning
clear target focus(es)
(inter)cultural / musical / linguistic cooperation between project partners on different levels

## Slide 32
Thank you for your attention!